## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project:
Week Of:
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
| 1 | Pitor |  | GUI elements (client side), Getting more cards to work (server side) | design and implementation other players' cards (client side)
| 2 | Samuel |  | Server for 4 playersor clients (server backend), waiting option if more than 4 players are already in the game | Testing
| 3 | Dean |  | logic for dealing the cards to the players, intgerates it to server and client | implementing server-client communication
| 4 | Justin |  | implemented betting in player class, integrate it into client gui, working on raising, matching and folding | Testing
Final Project Documentation | 5 | All